## Road Map
38 | Hearts & Paws
| Application Modules | Feature Backlog | Story Points (1-5) | SPRINT 1 | SPRINT 2 | SPRINT 3
|  |  |  | SPRINT1 - 03/25/2025 | SPRINT2 - 04/15/2025 | SPRINT3 - 05/06/2025
| 01. User Management | 01.01 Register Pet Adopter | 2 | X
|  | 01.02 Register Pet Owner | 2 | X
|  | 01.03 Register Service Provider | 2 | X
|  | 01.04 Login User | 3 | X
|  | 01.05 Edit Profile | 5 |  | X
|  | 01.06 View Profile | 3 | X
|  | 01.07 Recover Password | 4 |  |  | X
|  | 01.08 Delete Account | 3 |  |  | X
| 02. Pet Search | 02.01 Search by Category | 4 | X
|  | 02.02 Search by breed | 4 |  | X
|  | 02.03 Search by Gender | 3 |  |  | X
|  | 02.04 Search by Age | 3 |  |  | X
|  | 02.05 Search by City | 4 |  | X
|  | 02.06 Search by Activity Level | 4 |  |  | X
|  | 02.07 Search by Compatibility | 2 |  |  | X
| 03. Pet Listing | 03.01 Create Pet Profile | 4 | X
|  | 03.02 View Pet Profile | 2 | X
|  | 03.03 Edit Pet Profile | 5 | X
|  | 03.04 View Adoption Requests | 4 |  | X
|  | 03.05 Delete Pet Profile | 2 |  | X
|  | 03.06 Mark Pet adopted | 3 |  | X
03.07 List Temporary Foster Pets
| 04. Apointment Management | 04.01 Book Appointments | 5 | X
|  | 04.02 Cancel Appointments | 3 | X
|  | 04.03 View Appointment History | 3 |  |  | X
|  | 04.04 Rate and Review | 3 |  |  | X
|  | 04.05 Set Availability and Working hours | 2 | X
04.06 Sync Appointments with Calendars
| 05. Payments and Transactions | 05.01 Process Payments | 5 |  | X
|  | 05.02 View Transaction History | 3 |  | X
|  | 05.03 Generate invoices | 3 |  |  | X
|  | 05.04 Manage Refunds | 3 |  |  | X
05.05 Apply Promo Codes
| 06. Customer Support and Compliance | 06.01 Submit Support Tickets | 3 |  | X
|  | 06.02 Manage Support Tickets | 4 |  |  | X
|  | 06.03 Access FAQ & Knowledge Base | 2 |  | X
|  | 06.04 Manage Agreement | 3 |  | X
06.05 Join Community Forums
06.06 Monitor platform performance
06.07 Initiate Live Chat Support
|  |  | VELOCITY | 37 | 38 | 35

## Jira Road Map
Timeline/Roadmap View: Monthly
Timeline/Roadmap View: Weekly
Sprint 2 Sciped RoadMap

## Kanban Board
Kanban Board
Sprint 1
Sprint 2 Scoped
S2: Kanban Updates 4/7/25
S2: Kanban Update 4/14/25
S3: Kanban Update 4/28/25
S2: Kanban Updates 5/4/25