## S2
| Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
1 | 01. User Management | 1.05 | Edit Profile | Implement backend logic for profile update. | N | 3/26/2025 | 3/27/2025 | 100% | Rishita Gupta
2 | 01. User Management | 1.05 | Edit Profile | Develop frontend form for editing profile details. | N | 3/28/2025 | 3/30/2025 | 100% | Rishita Gupta
3 | 01. User Management | 1.05 | Edit Profile | Validate user input and handle errors. | N | 3/29/2025 | 3/30/2025 | 100% | Rishita Gupta
4 | 01. User Management | 1.05 | Edit Profile | Conduct exploratory tests for profile update. | N | 3/30/2025 | 3/31/2025 | 100% | Vishnu Vardan
5 | 02. Pet Search | 2.02 | Search by Breed | Design database query for searching pets by breed. | Y | 3/26/2025 | 3/26/2025 | 100% | Vrushali Tambat
6 | 02. Pet Search | 2.02 | Search by Breed | Implement backend API to fetch pet listings based on breed. | N | 3/28/2025 | 3/29/2025 | 100% | Vrushali Tambat
7 | 02. Pet Search | 2.02 | Search by Breed | Create frontend UI to allow users to select and search by breed. | N | 3/27/2025 | 3/28/2025 | 100% | Vrushali Tambat
8 | 02. Pet Search | 2.02 | Search by Breed | Conduct UI and API integration exploratory testing. | N | 3/29/2025 | 3/29/2025 | 100% | Lasya Priya
9 | 02. Pet Search | 2.05 | Search by City | Develop location-based pet search functionality. | N | 3/27/2025 | 3/28/2025 | 100% | Vrushali Tambat
10 | 02. Pet Search | 2.05 | Search by City | Implement API endpoint for city-based pet search. Implement API endpoint for city-based pet search. | N | 3/28/2025 | 3/29/2025 | 100% | Vrushali Tambat
11 | 02. Pet Search | 2.05 | Search by City | Integrate with frontend search filters. | N | 3/28/2025 | 3/29/2025 | 100% | Vrushali Tambat
12 | 02. Pet Search | 2.05 | Search by City | Conduct exploratory testing to test search performance and accuracy. | N | 3/29/2025 | 3/29/2025 | 100% | Lasya Priya
13 | 03. Pet Listing | 3.04 | View Adoption Requests | Create backend functionality to retrieve adoption requests. | N | 3/29/2025 | 3/30/2025 | 100% | Kunal Tajne
14 | 03. Pet Listing | 3.04 | View Adoption Requests | Develop UI for viewing and managing adoption requests. | N | 3/29/2025 | 3/30/2025 | 100% | Kunal Tajne
15 | 03. Pet Listing | 3.04 | View Adoption Requests | Exploratory testing to request retrieval and UI responsiveness. | N | 3/22/2025 | 3/23/2025 | 100% | Vishnu Vardan
16 | 03. Pet Listing | 3.05 | Delete Pet Profile | Allow authorized users to delete pet profiles with backend validation and logical deletion. | N | 4/3/2025 | 4/3/2025 | 100% | Rishita Gupta
17 | 03. Pet Listing | 3.05 | Delete Pet Profile | Update UI to include a delete button with confirmation. | N | 4/4/2025 | 4/6/2025 | 100% | Rishita Gupta
18 | 03. Pet Listing | 3.05 | Delete Pet Profile | Perform exploratory security tests to prevent unauthorized deletions. | N | 4/3/2025 | 4/4/2025 | 100% | Vishnu Vardan
19 | 03. Pet Listing | 3.06 | Mark Pet adopted | Implement backend logic to update pet adoption status. | N | 4/8/2025 | 4/10/2025 | 100% | Kunal Tajne
20 | 03. Pet Listing | 3.06 | Mark Pet adopted | Develop UI to allow users to mark a pet as adopted. | N | 4/10/2025 | 4/11/2025 | 100% | Kunal Tajne
21 | 03. Pet Listing | 3.06 | Mark Pet adopted | Send notification to the adopter when a pet is marked adopted. | Y | 4/11/2025 | 4/12/2025 | 100% | Kunal Tajne
22 | 03. Pet Listing | 3.06 | Mark Pet adopted | Exploratory testing to functionality to ensure status updates correctly reflect in the system. | N | 4/10/2025 | 4/12/2025 | 100% | Lasya Priya
23 | 05. Payments and Transactions | 5.01 | Process Payments | Integrate payment gateway for secure transactions. | Y | 3/25/2025 | 3/27/2025 | 100% | Ritik Kale
24 | 05. Payments and Transactions | 5.01 | Process Payments | Develop backend logic to process and validate payments. | N | 3/28/2025 | 3/31/2025 | 100% | Ritik Kale
25 | 05. Payments and Transactions | 5.01 | Process Payments | Implement error handling and rollback mechanism in case of failed transactions. | N | 4/2/2025 | 4/4/2025 | 100% | Ritik Kale
26 | 05. Payments and Transactions | 5.01 | Process Payments | Exploratory testing for payment processing with different scenarios. | N | 4/6/2025 | 4/10/2025 | 0% | Vishnu Vardan
27 | 05. Payments and Transactions | 5.02 | View Transaction History | Implement backend API to retrieve user transaction history. | N | 4/6/2025 | 4/7/2025 | 100% | Ritik Kale
28 | 05. Payments and Transactions | 5.02 | View Transaction History | Develop frontend UI to display past transactions. | Y | 4/8/2025 | 4/11/2025 | 0% | Ritik Kale
29 | 06. Customer Support and Compliance | 6.01 | Submit Support Tickets | Develop a support ticket submission form. | Y | 4/9/2025 | 4/11/2025 | 0% | Rishita Gupta
30 | 06. Customer Support and Compliance | 6.01 | Submit Support Tickets | Implement backend logic to store and track support requests. | N | 4/10/2025 | 4/11/2025 | 100% | Rishita Gupta
31 | 06. Customer Support and Compliance | 6.01 | Submit Support Tickets | Notify customer support agents when a ticket is submitted. | N | 4/10/2025 | 4/11/2025 | 0% | Rishita Gupta
32 | 06. Customer Support and Compliance | 6.03 | Access FAQ & Knowledge Base | Create a structured knowledge base with categorized FAQs. | Y | 4/8/2025 | 4/9/2025 | 0% | Vrushali Tambat
33 | 06. Customer Support and Compliance | 6.03 | Access FAQ & Knowledge Base | Develop UI for users to browse and search FAQs. | N | 4/9/2025 | 4/10/2025 | 0% | Vrushali Tambat
34 | 06. Customer Support and Compliance | 6.04 | Manage Agreement | Allow users to view and acknowledge terms & conditions. | Y | 4/5/2025 | 4/7/2025 | 0% | Kunal Tajne
35 | 06. Customer Support and Compliance | 6.04 | Manage Agreement | Develop an admin panel to update agreements. | N | 4/8/2025 | 4/11/2025 | 0% | Kunal Tajne

## S3
Module Name | RCT.ID | Core Feature | Task Description | Tracking in Jira (Y/N)? | Start Date | End Date | % Progress | Task Owner
01. User Management | 1.07 | Recover Password | Design “Forgot Password” UI with email input field (DEVELOPMENT) | N | 04-23-2025 | 04-25-2025 | 100% | Kunal Tajne
01. User Management | 1.07 | Recover Password | Create backend API to generate reset token and send email (DEVELOPMENT) | Y | 04-25-2025 | 04-27-2025 | 100% | Kunal Tajne
01. User Management | 1.07 | Recover Password | Implement token validation and password update logic (DEVELOPMENT) | y | 04-25-2025 | 04-27-2025 | 100% | Kunal Tajne
01. User Management | 1.07 | Recover Password | Test password reset with valid and invalid tokens (TESTING) | N | 04-27-2025 | 04-29-2025 | 100% | Deepak
01. User Management | 1.07 | Recover Password | Verify password strength and input validations (TESTING) | N | 04-27-2025 | 04-30-2025 | 100% | Vishnu
01. User Management | 1.07 | Recover Password | Ensure user receives reset email and it lands in inbox (TESTING) | N | 04-27-2025 | 04-30-2025 | 100% | Lasya
01. User Management | 1.07 | Recover Password | Produce Test Design Specification | N | 04-27-2025 | 04-30-2025 | 100% | Deepak
01. User Management | 1.07 | Recover Password | Produce Test Case Specification | N | 04-27-2025 | 04-30-2025 | 100% | Vishnu
01. User Management | 1.07 | Recover Password | Perform Testing | N | 04-27-2025 | 04-30-2025 | 100% | Lasya
01. User Management | 1.08 | Delete Account | Design account deletion confirmation UI (DEVELOPMENT) | N | 04-24-2025 | 04-25-2025 | 100% | Kunal Tajne
01.User Management | 1.08 | Delete Account | Implement delete account backend logic (DEVELOPMENT) | N | 04-24-2025 | 04-25-2025 | 100% | Kunal Tajne
01.User Management | 1.08 | Delete Account | Integrate frontend and backend for account deletion (DEVELOPMENT) | N | 04-25-2025 | 04-26-2025 | 100% | Kunal Tajne
01.User Management | 1.08 | Delete Account | Validate account deletion removes user data from DB (TESTING) | Y | 04-27-2025 | 04-30-2025 | 100% | Deepak
01.User Management | 1.08 | Delete Account | Test edge cases for delete account (TESTING) | N | 04-27-2025 | 04-30-2025 | 100% | Vishnu
01.User Management | 1.08 | Delete Account | Produce Test Design Specification | N | 04-28-2025 | 04-30-2025 | 100% | Lasya
01.User Management | 1.08 | Delete Account | Produce Test Case Specification | N | 04-28-2025 | 04-30-2025 | 100% | Deepak
01.User Management | 1.08 | Delete Account | Perform Testing | N | 04-27-2025 | 04-30-2025 | 100% | Vishnu
02. Pet Search | 2.03 | Search by Gender | Add gender filter dropdown in UI (DEVELOPMENT) | N | 04-18-2025 | 04-19-2025 | 100% | Vrushali Tambat
02.Pet Search | 2.03 | Search by Gender | Implement gender-based search filter in backend (DEVELOPMENT) | Y | 04-19-2025 | 04-20-2025 | 100% | Vrushali Tambat
02.Pet Search | 2.03 | Search by Gender | Test gender filter returns correct pet results (TESTING) | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02.Pet Search | 2.03 | Search by Gender | Produce Test Design Specification | N | 04-28-2025 | 2025-01-05 | 100% | Vishnu
02.Pet Search | 2.03 | Search by Gender | Produce Test Case Specification | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02.Pet Search | 2.03 | Search by Gender | Perform Testing | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02.Pet Search | 2.03 | Search by Gender | Verify UI filter updates search results live (TESTING) | Y | 04-28-2025 | 2025-01-05 | 100% | Deepak
02. Pet Search | 2.04 | Search by Age | Add age range slider or dropdown in UI (DEVELOPMENT) | Y | 04-18-2025 | 04-20-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.04 | Search by Age | Implement age filter logic in backend query (DEVELOPMENT) | N | 04-19-2025 | 04-20-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.04 | Search by Age | Test age filter with various values (TESTING) | N | 04-24-2025 | 04-29-2025 | 100% | Vishnu
02. Pet Search | 2.04 | Search by Age | Produce Test Design Specification | N | 04-24-2025 | 04-29-2025 | 100% | Deepak
02. Pet Search | 2.04 | Search by Age | Produce Test Case Specification | N | 04-24-2025 | 04-29-2025 | 100% | Vishnu
02. Pet Search | 2.04 | Search by Age | Perform Testing | N | 04-24-2025 | 04-29-2025 | 100% | Vishnu
02. Pet Search | 2.06 | Search by Activity Level | Define activity level categories (low, medium, high) (DEVELOPMENT) | N | 04-23-2025 | 04-24-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.06 | Search by Activity Level | Create activity filter component in UI (DEVELOPMENT) | N | 04-23-2025 | 04-25-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.06 | Search by Activity Level | Implement filtering based on activity level (DEVELOPMENT) | N | 04-25-2025 | 04-26-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.06 | Search by Activity Level | Verify filtered results match activity level selected (TESTING) | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02. Pet Search | 2.06 | Search by Activity Level | Produce Test Design Specification | N | 04-28-2025 | 2025-01-05 | 100% | Deepak
02. Pet Search | 2.06 | Search by Activity Level | Produce Test Case Specification | N | 04-28-2025 | 2025-01-05 | 100% | Vishnu
02. Pet Search | 2.06 | Search by Activity Level | Perform Testing | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02. Pet Search | 2.07 | Search by Compatibility | Design compatibility filter UI (kids, pets, environment) (DEVELOPMENT) | N | 04-26-2025 | 04-27-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.07 | Search by Compatibility | Implement compatibility logic in backend (DEVELOPMENT) | N | 04-26-2025 | 04-27-2025 | 100% | Vrushali Tambat
02. Pet Search | 2.07 | Search by Compatibility | Test compatibility combinations for correctness (TESTING) | N | 04-28-2025 | 2025-01-05 | 100% | Deepak
02. Pet Search | 2.07 | Search by Compatibility | Produce Test Design Specification | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
02. Pet Search | 2.07 | Search by Compatibility | Produce Test Case Specification | N | 04-28-2025 | 2025-01-05 | 100% | Deepak
02. Pet Search | 2.07 | Search by Compatibility | Perform Testing | N | 04-28-2025 | 2025-01-05 | 100% | Deepak
04.Appointment Management | 4.03 | View Appointment History | Fetch appointment data from DB for logged-in user (DEVELOPMENT) | N | 04-24-2025 | 04-25-2025 | 100% | Rishita Gupta
04.Appointment Management | 4.03 | View Appointment History | Test history loads correct appointments (TESTING) | N | 04-26-2025 | 04-30-2025 | 100% | Vishnu
04.Appointment Management | 4.03 | View Appointment History | Produce Test Design Specification | N | 04-26-2025 | 04-30-2025 | 100% | Deepak
04.Appointment Management | 4.03 | view Appointment History | Produce Test Case Specification | N | 04-26-2025 | 04-30-2025 | 100% | Vishnu
04.Appointment Management | 4.03 | View Appointment History | Perform Testing | N | 04-26-2025 | 04-30-2025 | 100% | Vishnu
04.Appointment Management | 4.04 | Rate and Review | Add rating & review form in UI (DEVELOPMENT) | Y | 04-28-2025 | 04-29-2025 | 100% | Rishita Gupta
04.Appointment Management | 4.04 | Rate and Review | Create API to submit and store reviews (DEVELOPMENT) | N | 04-29-2025 | 04-30-2025 | 100% | Rishita Gupta
04.Appointment Management | 4.04 | Rate and Review | Test form validation and rating submission (TESTING) | N | 04-30-2025 | 2025-02-05 | 100% | Lasya
04.Appointment Management | 4.04 | Rate and Review | Produce Test Design Specification | N | 04-30-2025 | 2025-02-05 | 100% | Lasya
04.Appointment Management | 4.04 | Rate and Review | Produce Test Case Specification | N | 04-30-2025 | 2025-02-05 | 100% | Deepak
04.Appointment Management | 4.04 | Rate and Review | Perform Testing | N | 04-30-2025 | 2025-02-05 | 100% | Lasya
05. Payments and Transactions | 5.03 | Generate Invoices | Design invoice format template (DEVELOPMENT) | Y | 04-24-2025 | 04-26-2025 | 100% | Ritik Kale
05. Payments and Transactions | 5.03 | Generate Invoices | Implement invoice generation after transaction (DEVELOPMENT) | N | 04-24-2025 | 04-26-2025 | 100% | Ritik Kale
05. Payments and Transactions | 5.03 | Generate Invoices | Validate invoice content and format (TESTING) | N | 04-27-2025 | 2025-01-05 | 100% | Vishnu
05. Payments and Transactions | 5.03 | Generate Invoices | Produce Test Design Specification | N | 04-27-2025 | 2025-01-05 | 100% | Deepak
05. Payments and Transactions | 5.03 | Generate Invoices | Produce Test Case Specification | N | 04-28-2025 | 2025-01-05 | 100% | Deepak
05. Payments and Transactions | 5.03 | Generate Invoices | Perform Testing | N | 04-27-2025 | 2025-01-05 | 100% | Vishnu
05. Payments and Transactions | 5.04 | Manage Refunds | Create refund request UI (DEVELOPMENT) | N | 04-25-2025 | 04-26-2025 | 100% | Ritik Kale
05. Payments and Transactions | 5.04 | Manage Refunds | Implement refund logic and status tracking (DEVELOPMENT) | N | 04-26-2025 | 04-27-2025 | 100% | Ritik Kale
05. Payments and Transactions | 5.04 | Manage Refunds | Test refund submission and processing (TESTING) | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
05. Payments and Transactions | 5.04 | Manage Refunds | Produce Test Design Specification | N | 04-28-2025 | 2025-01-05 | 100% | Vishnu
05. Payments and Transactions | 5.04 | Manage Refunds | Produce Test Case Specification | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
05. Payments and Transactions | 5.04 | Manage Refunds | Perform Testing | N | 04-28-2025 | 2025-01-05 | 100% | Lasya
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Create admin view to manage support tickets(DEVELOPMENT) | Y | 04-17-2025 | 04-20-2025 | 100% | Rishita Gupta
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Enable admin to update ticket status (Open, In Progress, Resolved, Closed) (DEVELOPMENT) | N | 04-21-2025 | 04-23-2025 | 100% | Rishita Gupta
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Test ticket filtering and sorting (TESTING) | N | 04-24-2025 | 04-29-2025 | 100% | Deepak
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Test ticket reply flow and verify responses show correctly (TESTING) | N | 04-24-2025 | 04-29-2025 | 100% | Vishnu
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Validate admin status updates and agent assignments (TESTING) | N | 04-25-2025 | 04-29-2025 | 100% | Lasya
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Produce Test Design Specification | N | 04-25-2025 | 04-29-2025 | 100% | Vishnu
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Produce Test Case Specification | N | 04-25-2025 | 04-29-2025 | 100% | Vishnu
06. Customer Support and Compliance | 6.02 | Manage Support Tickets | Perform Testing | N | 04-25-2025 | 04-29-2025 | 100% | Lasya